## Product Requirements & Diagnost (hidden)
Questions | Responses
Describe the primary use cases (real-world application) for your solution. Include here both actual and potential use cases of your solution. Please provide data/results of any pilots. For each actual and potential use case, provide an explanation why you feel the technology is suitable for this use case.
Does your product serve users that are less than 35 years old?
What is the age range of your users?
Describe the current and projected number of these users that your product serves (i.e. your reach)
Please choose the most relevant technology category (/ies) for your solution and complete questions on either
What are the features within your solution that you will develop / refine / test over the next six (6) months? Include the status of the feature (developing, refining etc. )
Prototyping: Describe the work you have done on proofs of concept, mockups, and user testing. List the last three versions of your solution’s design. For each version, please provide 2 sentences that describe the reasons for the changes (including data) and outline the main changes made.
Before you developed your own, what other similar technologies did you consider using, improving or iterating to solve the problem you want to solve? Outline what other technologies were considered to address the problem you identified and why were they rejected as unsuitable.
Please select the license type that your solutions are currently registered under.
If currently not on an open source license, are you willing to release your tech solution under an AGPL, LGPL, BSD or equivalent open-source license
Please submit a document with a diagram of your current tech stack including all components and subsystems, showing their linkages and interactions. A tech stack is a combination of software products and programming languages used. For this diagram, include: both client side and server side documentation if relevant, tools used for front-end and back-end systems (including databases), and any meta-layers. If you are using machine learning, please describe your pipeline.
Where do you host the repositories of your solution?
Please share the github / bitbucket (or other) handles of the code developers within your team
How many external contributors have there been to your code?
Please share the stack overflow profile (or equivalent) of the code developers within your team (if available)?
What processes and tools do you leverage for quality assurance and testing?
What version control system do you use?
Sustainability: What is the ongoing plan for maintenance, updates, and support of your software? Describe what the needs will be for the next two years and how these will be met.
Is your startup using data as a central part of the solution?
Describe your data sets (i.e. size, features, method of collection, labels) If applies, please also include the description of the test and training data sets.
Describe how you already collect or plan to collect data and with which technologies.
Describe who is the owner of the data and what licenses is it under.
If you use personally identifiable indicators, please describe how you secure the privacy of individuals
Does your startup use artificial intelligence or machine learning?
Describe your models and why you settled on using them. (E.g. we use Logistic Regression because it is easy to interpret and we don't have enough data to use more sophisticated methods).
How do you evaluate your models / methods? (i.e. accuracy, F1 score, Regression coefficient)
Describe your roadmap to further improving your model and how you plan to maintain it and keep it up-to-date?
Describe the limitations of your methodology: Where does your approach fail? (e.g. your predictions are biased because you do not have enough data for a certain class)
Is your startup using Blockchain?
What blockchain platform are you using? (ie. Bitcoin, Ethereum, Hyperledger, etc). Please explain your choice and clarify whether it is a private or public chain
Is your product deployed? If so, where? (ie. private node, mainnet, test net)
What consensus algorithm does the blockchain you’re using use? (ie. Proof of Work, Proof of Stake, Delegated Proof of Stake)
What language are you using to create your smart contracts? (ie. Solidity, Lvy, Viper).
How do you go about testing your smart contracts?
Is personal/biometric data being stored in the blockchain? If yes, how are you ensuring the privacy of that data?
Link to Diagnostic Tool

## Project Resources
Document / Resource | Link
Pitch Deck | Codesrock pitchdeck (2) - Triumph Tetteh.pdf
Company 1 pager | Codesrock Labs- One Pager
Needs Assessment Survey | Codesrocks Labs- Needs Assessment Survey
Business Diagnostic Tool | Codesrock Labs Business Diagnostics Tool
Product Questionnaire | Codesrock Labs - Product Requirement Questionnaire

## Project 1 - Broad Strategy By E
-
| Startup Name | Codesrock Labs
| Coach/Expert | Bright Ahedor and Edwin Butler
| Project Name (Prioritised area of need) | Product Development and Operational Excellence
| Strategy/Solution Areas | - Product Development and Market Readiness | - Operational Excellence and Brand Visibility
| KPIs | - Review, edit, and finalize all 46 lesson video contents, and complete their upload to the platform by 20 June 2026. -Complete the development of the portal by delivering 100% of the approved features, conducting end-to-end testing, resolving all critical and high-priority bugs, and achieving production readiness by 30th June, 2026. - Successfully launch the teacher portal on 15th August, 2026, onboard 4 teachers from 2 partner schools, for testing and achieve active platform adoption, core module completion, and initial student progress tracking. | - Develop an SOP to audit and close all operational gaps -Deliver a virtual platform launch campaign that strengthens brand visibility and engagement by attracting at least 50 targeted participants to the launch event and converting visibility into at least 5 school sign-ups and 5 parent ambassador registrations.
| Description of Strategy & Outcomes | CodesRock Labs moves from informal, untrackable in-person and YouTube-based teacher training to a professional, data-rich learning management system that the company fully owns and controls. Teacher quality is measurable and improvable. Student progress is captured at scale. The portal becomes a core differentiator in school partnership conversations — "we don't just give you a robot, we give you a professionally trained, tracked, and evaluated teacher" — and a compelling demonstration asset for investors and grant applications. | CodesRock Labs will possess a clear, team-wide operational "playbook." Every team member — current and future — will know exactly what their role is, what great performance looks like, and how their work connects to the company's mission. This removes dependency on informal knowledge, ensures consistent delivery quality across all nine school partnerships, and creates the infrastructure for scaling to 150+ schools without losing quality or founder involvement in day-to-day decisions.
| Resources required to implement the Strategy | Development team: final QA sprint and bug fixes before launch Server/hosting infrastructure ( and database) (Render, Supabase — budget for monthly hosting cost) Teacher onboarding guide: written PDF + 2-minute video walkthrough screencast Dedicated support channel (WhatsApp group or email) for teacher portal queries Launch communication materials: email templates, WhatsApp messages for school partners Analytics access to track completion rates, evaluation scores, and login activity | 2–3 days of focused founder time (co-design sessions to map the pipeline end-to-end) Documentation tool: Notion (recommended — free, collaborative), or Google Docs Input sessions with each current team member to capture their actual workflows A process-mapping template or whiteboard session (physical or digital using Miro/FigJam) Optional: a part-time operations consultant or UNICEF-connected mentor for 1–2 review sessions
| Partnerships | Association of Private Schools
Other
Other
Other

## Detailed Workplan
Project Duration - 5 months May 1 to September 30, 2026
| KPIs | Specific Activities | Responsible | Start Date | End Date | Status | Link to Documents | Comments/Notes
| Developing and Integrating high quality tutorial videos into the teacher hub | Film all episodes of Codesrock 1 training videos | Ellen | 2026-04-23 | 2026-06-06 | Completed
|  | aligning videos with curriculum and sorting out videos and audio combinations | Triumph | 2026-06-01 | 2026-06-08 | Completed | Aligning audios, visuals and curriculum structure
|  | Create an absolute documentation to guide edit and include the necessary animation and brand guide | Triumph | 2026-06-08 | 2026-06-13 | Completed | Aligning audios, visuals and curriculum structure | There was a significant delay. Though the video shoot is complete the audio and video components are separate and weren't named properly. Due to this I have to take time to organize and pair the components so the editors can effectively do their edits
|  | Edit first batch epsideos for Codesrock 1 training videos | Felix | 2026-06-24 | 2026-06-28 | Completed | https://www.youtube.com/playlist?list=PLXHWi1MOerP0mo7Ur69br3gnLA99-rn1P
|  | Upload and integrate first batch of episodes of Codesrock 1 training videos | Triumph | 2026-06-29 | 31-06-2026 | Completed | snapshots showing uploads on codesrock
Product | KPI - Portal development 100% complete: all features built, tested, and bugs resolved | Onboard already trained teachers to beta test the platform | Triumph | 2026-06-26 | 2026-06-25 | Completed
|  | Fix all critical bugs; assign non-critical bugs to a post-launch sprint | Triumph | 2026-06-22 | 2026-05-29 | Completed
|  |  | Ellen |  |  | Completed
| KPI - Official launch date confirmed and communicated to all partner schools | Set a hard, specific launch date — put it in writing and share with all 9 school partners | Triumph | 2026-07-01 | 2026-06-02 | Completed |  | Launch date changed to mid July to give sufficient time for campaign hype and achieve visibility KPIs
|  | Create the teacher onboarding pack: a clear, jargon-free written guide AND a 2–3 minute screen-recorded video walkthrough | Triumph | 2026-06-19 | 2026-06-22 | Completed
| KPI - Teacher onboarding pack created (written guide + video walkthrough) | Set up portal accounts for every teacher at all 9 partner schools (do not wait for them to self-register)
|  | Host a "Portal Launch Day" — a 30-minute virtual or in-person session where all teachers log in for the first time together | Winnifred | 2026-07-10 | 2026-07-10 | Not Started
|  | Set up a dedicated WhatsApp support group for portal questions and technical issues | Winnifred | 2026-05-27 | 2026-06-28 | Completed
| KPI - % of current partner school teachers with active portal accounts | Set a 30-day milestone: all enrolled teachers must complete the core modules — follow up personally with anyone who hasn't | Ellen | 2026-05-15 | 2026-07-15 | Completed
|  | Track portal analytics weekly: which modules have the lowest completion rates? Investigate and simplify | Ellen | 2026-05-15 | 2026-06-18 | Not Started
|  | At 60 days post-launch, send a survey to all teachers: what's working, what's confusing, what's missing? | Ellen | 2026-08-12 | 2026-08-20 | Not Started
|  | Formally communicate the YouTube-to-portal transition: set a date after which the portal is the primary resource and YouTube is supplementary only | Ellen | 2026-08-24 | 2026-08-25 | Not Started
Business / Other | KPI - Operational pipeline document completed and approved by both co-founders | Draft the initial version of the operational pipeline document based on the co-founders' mapping session. |  | 2026-05-20 | 2026-05-20 | Completed
|  | Identify and document the current operational bottleneck in the pipeline |  | 2026-05-20 | 2026-05-20 | Completed
|  | Draft a comprehensive outline for the operational pipeline document, including key stages from lead generation to certification. |  | 2026-05-20 | 2026-05-20 | Completed
|  | Block one full day for both co-founders to map every activity from "school lead generated" to "school certified" on a whiteboard or Miro board or notion | Ellen | 2026-05-20 | 2026-05-22 | Completed
|  | Review the drafted operational pipeline with the other co-founder for final approval and sign-off |  | 2026-05-20 | 2026-05-20 | Completed
|  | Identify and document the core objectives and key performance indicators (KPIs) for the operational pipeline with both co-founders. |  | 2026-05-20 | 2026-05-20 | Completed
| KPI -Number of pipeline stages fully documented with owner, SOP, and success criteria | List every team member's current role and the activities they own day-to-day | Triumph | 2026-05-15 | 2026-05-18 | Completed
|  | For each pipeline stage, appoint a named "Stage Owner" who is accountable for delivery | Triumph | 2026-05-18 | 2026-05-19 | Completed
|  | Write each stage as a 1-page Standard Operating Procedure (SOP): Who does what, by when, using which tools, and how success is measured | Triumph | 2026-05-19 | 2026-05-22 | Completed
| KPI - Performance threshold defined for each pipeline stage | To Do
To Do
To Do
|  | Define at least 5 performance thresholds (e.g., "Teacher training must achieve ≥85% proficiency; hardware deployed within 5 days of school sign-off") | Triumph | 2026-05-25 | 2026-05-27 | Completed
|  | Share the draft pipeline document with the full team for review and input (allow 3 days for feedback) | Triumph | 2026-05-27 | 2026-06-01 | Completed
| KPI - Team SOP compliance rate (% of staff following the documented process) | To Do
To Do
To Do
To Do
|  | Finalise and version-control the document (label it v1.0 with the date) | Triumph | 2026-06-02 | 2026-06-03 | Completed
|  | Store the document in a shared, accessible location (Google Drive or Notion workspace) | Triumph | 2026-06-03 | 2026-06-04 | Completed
| KPI - Pipeline reviewed and updated (quarterly cycle) | 0n | Triumph | 2026-06-26 | 2026-06-26 | Completed
To Do
To Do
|  | Identify areas of friction in the current workflow and suggest process improvements based on quarterly review findings | %completion |  |  | 86.6667

## Project 1 (Product) - Monthly A
KPI | MAY
| Week 1 Activity | Status | Week 2 Activity | Status | Week 3 Activity | Status | Week 4 Activity | Status | Execution %
Complete development of teacher hub MVP, test every screen, every user journey (teacher, admin, student view) — document all bugs | Authentication, Onboarding, & Core Dashboards (All Roles) Objective: Verify initial access paths, onboarding flows, and the layout integrity of the main user dashboards. | Completed | Review development and take feedback from supervisors | Completed | upload placeholder videos and test all functionalities and pages related to the videos | Completed | Create documentation for the animation team to guide their animation or motion graphics work | Completed | 100
| Class Management & Student Tracking (Teacher Journey) Objective: Thoroughly test the classroom roster system, student enrollment, progress updates, and reporting. | Completed | Improve critical features and the overall usability of the application | Completed | Test the functionality of XP points, streaks and every gamified activity related to completing videos | Completed |  | Completed
| Learning Path, Resource Library, & Calendar (Teacher & Student) Objective: Validate course progression, video playback metrics, resource sharing, and training events. | Completed | Test application, document bugs and needed fixes | Completed | Document all functionalities related to video and gamification that require fixing or improvement | Completed |  | Completed
|  | Completed |  | Completed |  | Completed |  | Completed
Recording of Codesrock 1 Videos |  | Completed |  | Completed |  | Completed |  | Completed
| Outline of videos/topics to be covered in deliverables | Completed | Record coding mat activity videos | Completed | Record activity action songs videos | Completed | Recording activity book videos | Completed
| Schedule time in Starters Hub studio and align with all menbers of the team for shoot | Completed | Review of coding mat videos and do reshoots | Completed | Review of activity mat videos and do reshoots | Completed | Review of activity book videos and do reshoots | Completed
|  | Completed |  | Completed |  | Completed |  | Completed
|  | Completed |  | Completed |  | Completed |  | Completed
|  | 100% | % completion | 100% | % completion | 100% | % completion | 100%
KPI | JUNE
| Week 1 Activity | Status | Week 2 Activity | Status | Week 3 Activity | Status | Week 4 Activity | Status | Execution %
- Preparing teacher hub/portal for the official launch | Schedule date with Mohdlana Preschool for beta testing | Completed |  | Completed | Create the teacher onboarding pack: a clear, jargon-free written guide AND a 2–3 minute screen-recorded video walkthrough | Completed | Get teacher feedback on the initial use of the teacher hub | Completed | 100
| Evaluations, Certificates, & Gamification Integrity (Teacher & Student) Objective: Verify the assessment engine, automated credentials, and the gamification leaderboard. | Completed | Fix any citical bugs that arise as a result on the beta testing | Completed | Set up a dedicated WhatsApp support group for portal questions and technical issues | Completed | Document bugs and setbacks upon beta testing by teachers | Completed
| Set a hard, specific launch date — put it in writing and share with all 9 school partners | Completed | Create survey form to collect data on teacher use of the teacher hub | Completed | onboard Mohdlana preschool teachers at beta testers | Completed |  | Completed
Finish Recording and Edit Codesrock 1 Videos and beta test Codesrock teacher hub with real users | Record robot activity videos | Completed | Record all introduction and setup videos | Completed | Record all tips videos | Completed | Edit first set of codesrock 1 videos to get them ready for upload to officially onboard teacher for beta testing of application | Completed
| Review robot activity videos and do reshoots | Completed | Review intro videos and do reshoots where needed | Completed | Review all videos and make necessary reshoots and audio recordings | Completed | Upload of first set of codesrock 1 unto youtube and link added to lessons on teacher portal | Completed
| Create intro and outro codesrock animation | Completed | Communicate with client(school) when onboarding of their teachers will take place and the context of the onboarding | Completed | Document all videos, pair with their audios, align them with the course structure | Completed | Onboard first 4 teachers from Mohdlana to Beta test the application | Completed
| Finalize date on when to onboard teachers for beta testing | Completed | Draft milestones to be achieved upon unboading |  | Create quiz documentation for all lessons in Codesrock 1 in the order of the course structure | Completed | Document all setbacks and bugs that needs to fixed | Completed
| % completion | 100% | % completion | 100% | % completion | 100% | % completion | 100%
KPI | JULY
| Week 1 Activity | Status | Week 2 Activity | Status | Week 3 Activity | Status | Week 4 Activity | Status | Execution %
Preparation for the Official launch of teacher hub, | Set a 30-day milestone: all enrolled teachers must complete the core modules — follow up personally with anyone who hasn't | In Progress | Actively engage enrolled teachers on milestones set. Discover any challenges that exist and device plans to fix or abate such challenges |  | Create a reward system to make XP points collected by teacher more real and encourage them to use the application and collect student data |  | Start implementation of reward system for teachers and schools to encourage active use of Teacher Hub |  | 0
Get testominals
fixing all teacher hub bugs, upgrading content on teacher hub, and monitoring and evaluation teacher, data collection , analysis and improvement of teacher hub | Edit 2nd batch Codesrock 1 videos | In Progress | Track portal analytics weekly: which modules have the lowest completion rates? Investigate and simplify |  | Edit 4th (final) batch of Codesrock 1 videos
| Review, upload and integrate 2nd batch of edited videos. |  | Populate teacher hub with resources and other non-critical requirements |  | Review, upload and integrate 4th(final) batch
| Setup analytics to track use of teacher hub | In Progress | Audit management controls, data aggregation dashboards, and compile regression test results. |  | Review all quiz questions and make changes, additions or subtractions where needed
| Improve student tracking by adding more and better parameters | In Progress | Edit 3rd batch of Codesrock 1 videos |  | Start analyzing data from teacher hub and set benchmarks
| Upload quiz questions for 2nd batch of edited videos/lessons | In Progress | Review, upload and integrate 3rd batch of edited videos. |  | test teacher hub to detect any bugs and obvious feature improvements needed. Document all bugs and improvements requires since all codesrock 1 videos and quizes are setup
| % completion | 0% | % completion | 0% | % completion | 0% | % completion | 0%
KPI | AUGUST
| Week 1 Activity | Status | Week 2 Activity | Status | Week 3 Activity | Status | Week 4 Activity | Status | Execution %
Scaling teacher hub to more users | [8 empty] | 0
Development and testing of Codesrock 2 curriculum and content
| % completion | 0% | % completion | 0% | % completion | 0% | % completion | 0%
KPI | SEPTEMBER
| Week 1 Activity | Status | Week 2 Activity | Status | Week 3 Activity | Status | Week 4 Activity | Status | Execution %
Reviewing teacher reward system on the teacher hub to boost teacher engagement | [8 empty] | 0
Launch and distribution of Codesrock 2 Creation of Codesrock 2 content for Teacher Hub
| % completion | 0% | % completion | 0% | % completion | 0% | % completion | 0%

## Project 2 (Business) - Monthly
MAY
| Week 1 Activity | Status | Week 2 Activity | Status | Week 3 Activity | Status | Week 4 Activity | Status | Execution %
Develop and Document an SOP for Codesrock Labs | Draft the initial version of the operational pipeline document based on the co-founders' mapping session. | Completed | Identify and document the core objectives and key performance indicators (KPIs) for the operational pipeline with both co-founders. | Completed | Define at least 5 performance thresholds (e.g., "Teacher training must achieve ≥85% proficiency; hardware deployed within 5 days of school sign-off") | Completed | Finalise and version-control the document (label it v1.0 with the date) | Completed | 100
| Identify and document the current operational bottleneck in the pipeline | Completed | List every team member's current role and the activities they own day-to-day | Completed | Review the finalized pipeline document with both co-founders to secure formal sign-off and approval. | Completed | Store the document in a shared, accessible location (Google Drive or Notion workspace) | Completed
| Draft a comprehensive outline for the operational pipeline document, including key stages from lead generation to certification. | Completed | For each pipeline stage, appoint a named "Stage Owner" who is accountable for delivery | Completed |  | Completed |  | Completed
|  | Completed |  | Completed |  | Completed |  | Completed
Get a fair evaluation of the current brand visility of codesrock labs |  | Completed |  | Completed |  | Completed |  | Completed
|  | Completed |  | Completed |  | Completed |  | Completed
|  | Completed |  | Completed |  | Completed |  | Completed
|  | Completed |  | Completed |  | Completed |  | Completed
|  | Completed |  | Completed |  | Completed |  | Completed
| % completion | 100% | % completion | 100% | % completion | 100% | % completion | 100%
KPI | JUNE
| Week 1 Activity | Status | Week 2 Activity | Status | Week 3 Activity | Status | Week 4 Activity | Status | Execution %
Audit current operations, identify gaps and implement solutions . | Schedule a monthly 30-minute Pipeline Review meeting on the team calendar | Completed | Prepare survey for each Codesrock client, ambassador and for Pilots to collect data | Completed | Document detailed plan and agenda for codesrock brand visibility using the codesrock teacher hub/portal launch | Completed | Conduct survey for Codesrock schools (teachers and school heads) | In Progress | 61.1111
| Have first pipleline review meeting to identify initial gaps | Completed | Assign person to responsiblity for gaps that exist after first review | Completed | Develop a survey that will be used to evaluate codesrock's operations excellence with clients | Completed | Identify and document any operational gaps that exist based on survey collected from Codesrock schools | In Progress
| Document existing gaps and review treshold documented in SOP for each acitivity related to the gap | Completed
outline plan for codesrock brand visibility using | Record robot activity videos | Completed | Record all introduction and setup videos | Completed | Record all tips videos | Completed | Edit first set of codesrock 1 videos to get them ready for upload to officially onboard teacher for beta testing of application | Completed
| Review robot activity videos and do reshoots | Completed | Review intro videos and do reshoots where needed | Completed | Review all videos and make necessary reshoots and audio recordings | Completed | Upload first set of coodesrock 1 videos to admin portal and beta test teacher hub | Completed
| Create intro and outro codesrock animation | Completed | Communicate with client(school) when onboarding of their teachers will take place and the context of the onboarding | Completed | Document all videos, pair with their audios, align them with the course structure | Completed | Onboard Mohdlana Codesrock teacher to beta test Teacher Hub with new content uploaded | Completed
| Finalize date on when to onboard teachers for beta testing | Completed | Draft milestones to be achieved upon unboading | Completed | Structure modules based on video and develop Quizes for each stage of the module | Completed
| % completion | 100% | % completion | 66.67% | % completion | 66.67% | % completion | 33.33%
KPI | JULY
| Week 1 Activity | Status | Week 2 Activity | Status | Week 3 Activity | Status | Week 4 Activity | Status | Execution %
Launch campaign | review current progress and set or reschedule date for Launch | [7 empty] | 0
Launch campaign aimed at improving brand visibility
| % completion | 0% | % completion | 0% | % completion | 0% | % completion | 0%
KPI | AUGUST
| Week 1 Activity | Status | Week 2 Activity | Status | Week 3 Activity | Status | Week 4 Activity | Status | Execution %
Teacher Hub Launch campaign and Launch | [8 empty] | 0
converting leads to clients Reviewng and improving sales pipe line based on campaign results
| % completion | 0% | % completion | 0% | % completion | 0% | % completion | 0%
KPI | SEPTEMBER
| Week 1 Activity | Status | Week 2 Activity | Status | Week 3 Activity | Status | Week 4 Activity | Status | Execution %
Improving Teacher Hub based on analytics | [8 empty] | 0
Improving sales pipeline
| % completion | 0% | % completion | 0% | % completion | 0% | % completion | 0%

## Budget
Prototyping Fund Budget |  |  |  |  | COST
KPI | Activity | Expense Item | Link to Relevant Documents | Link to Relevant Documents | August | September | October | November | TOTAL
KPI 3.3 — Teacher Portal Launch Target: Portal live by Sep ¦ 100% of partner schools onboarded by Oct ¦ 80% teacher activation
| Final QA & Bug Fixes | External developer — QA sprint & fixes (contract) |  |  | 5000 |  |  |  | 5000
| Portal Infrastructure | Web hosting & domain renewal (annual, GHS) |  |  | 870 |  |  |  | 870
| Portal Infrastructure | SSL certificate & security setup |  |  | 400 |  |  |  | 400
| Portal Infrastructure | Monthly hosting / bandwidth charges |  |  |  | 900 | 900 | 900 | 2700
| Content Development(new content) and Migration (old content) (YouTube → Portal) | Data/internet costs for upload & migration |  |  | 3000 | 3000 |  |  | 6000
| Content Migration (YouTube → Portal) | Video editing & thumbnails (freelancer) |  |  | 1500 | 1500 |  |  | 3000
| Portal Launch Event | Venue hire (school hall / community space) |  |  |  | 1500 |  |  | 1500
| Portal Launch Event | Catering & refreshments |  |  |  | 800 |  |  | 800
| Portal Launch Event | Roll-up banners & branded materials (print) |  |  |  | 1500 |  |  | 1500
| Portal Launch Event | Invitations, flyers & digital comms |  |  |  | 200 |  |  | 200
| School Onboarding & Teacher Training | Transport to 9 schools for onboarding visits |  |  |  | 1200 | 1200 |  | 2400
| School Onboarding & Teacher Training | Printed teacher guides & training materials |  |  |  | 850 |  |  | 850
| School Onboarding & Teacher Training | Teacher onboarding workshop facilitation costs |  |  |  | 600 | 600 |  | 1200
| Impact Measurement | Post-launch survey tools & analysis | [5 empty] | 350 | 350
SUBTOTAL — 3.3 Teacher Portal Launch |  |  |  |  | 10770 | 12050 | 2700 | 1250 | 26770
KPI 3.3B — Brand Visibility through Teacher Portal Launch Target: ≥3 earned media placements ¦ ≥50% social engagement lift vs. baseline ¦ measurable Ambassador sign-up spike during launch window | Brand Visibility — Press/PR, social amplification, ambassador activation & visibility assets tied to the Portal launch
3.3B | Media & PR | Press & media kit design (graphic designer, one-time) |  |  | 2000 |  |  |  | 2000
| Media & PR | Press release distribution & local media outreach |  |  |  | 2000 |  |  | 2000
| Media & PR | Journalist/blogger launch-day invitations & briefing materials |  |  |  | 1000 |  |  | 1000
| Social Media Amplification | Launch content production — graphics & short-form video (freelancer) |  |  | 4000 | 3000 |  |  | 7000
| Social Media Amplification | Paid social boost — brand visibility campaign (FB/IG/TikTok) |  |  |  | 5000 | 5000 | 5000 | 15000
| Social Media Amplification | Launch hashtag campaign & landing page microsite design |  |  | 300 |  |  |  | 300
| Ambassador & Community Activation | Parent Ambassador launch recruitment push — referral bonus top-up window |  |  |  | 3000 |  |  | 3000
| Ambassador & Community Activation | Partner-school spotlight & Showcase Day content (photo + video coverage) |  |  |  |  | 1500 |  | 1500
| Visibility Assets | CodesRock Schools Directory listing — design & publish |  |  |  | 500 |  |  | 500
| Visibility Assets | UNICEF Cohort 6 / NaCCA co-branding assets (digital badges, signage refresh) |  |  |  |  | 10000 |  | 10000
SUBTOTAL — 3.3B Brand Visibility & Market Awareness |  |  |  |  | 6300 | 14500 | 16500 | 5000 | 42300
KPI 1.1 — Full pipeline mapped end-to-end Target: Complete 'lead generated → school certified' pipeline map by end of August | Step 1 — Block one full day for both co-founders to map every pipeline activity on a whiteboard or Miro board
Step 1 | Full-day co-founder mapping session | Miro Board — Pro plan subscription (monthly) | Strategic Priority Plan |  | 300 | 300 | 300 | 300 | 1200
| Full-day co-founder mapping session | Whiteboard, sticky notes & stationery supplies |  |  | 400 |  |  |  | 400
| Full-day co-founder mapping session | Venue hire for offsite working session |  |  | 1000 |  |  |  | 1000
| Full-day co-founder mapping session | Catering & refreshments (full-day session) |  |  | 3000 |  |  |  | 3000
SUBTOTAL — Step 1: Pipeline Mapping Session |  |  |  |  | 4700 | 300 | 300 | 300 | 5600
GRAND TOTAL (GHS) |  |  |  |  | 21770 | 26850 | 19500 | 6550 | 74670

## Project ResourcesDocuments
Document name | link
SOP Document | Codesrock Operations
Codesrock 1 recordings (raw files) | Raw video and audios
Aligning audio, visuals, and curriculum structure | Audio_Video_Matching_Table
First batch of tutorials for upload to beta test | Computational Thinking
First batch of tutorials uploaded to youtube | https://www.youtube.com/playlist?list=PLXHWi1MOerP0mo7Ur69br3gnLA99-rn1P
First batch of tutorials uploaded to Teacher hub/portal | snapshots showing uploads on codesrock
Beta onboarding and testing (event pictures) | Beta onboarding and testing with Mohdlana
Survey forms | https://form.jotform.com/261747723063055 https://form.jotform.com/261748216423053 https://form.jotform.com/261748122730050
Bug Report | Teacher_Hub_Bug_Report_Fix_Plan.docx

## Research & Impact
|  | USERS/ CUSTOMERS | [5 empty] | PARTNERSHIPS |  | INVESTMENT AND REVENUE |  |  | EMPLOYEES
Year | Month | Total Number of New users | Number of Males | Number of Females | Number of Not disclosed | Number in Rural Areas | Number who are PWD | Number of New Partnerships | Nature of Partnerships (Brief details of the partnership) | Amount of New Investment Raised (equity, debt, grant funding in US$) | Types of Investors (equity, debt, grant funding) | Monthly Revenue (GHS) | Number of New Employees Hired | Number of New Women Employees Hired | Number of New Youth (18-35) Hired | Number of Emlpoyee who are PWD | New Employees salary or salary ranges (GHS) | Key Services & Benefits to Employees
2026 | January
2026 | February
2026 | March
2026 | April
2026 | May
2026 | June
2026 | July
2026 | August
2026 | September
2026 | October
2026 | Novemeber
2026 | December
Totals |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Portfolio Booklet 26
Startup Name | Date Founded | Website | Location | Number of Employees | Industry | Email | Problem Statement & Solution | Description of Startup's Product | Key Members of Startup's Team | Products & Services | Milestones Achieved by Startup | Growth Strategy | StartUp Lab Impact Statement | Social Media Handles
Codesrock Labs | 2025 | https://codesrock.com/ | Greater Accra Region | 7 | Education Technology | hello@codesrock.com triumphtetteh@gmail.com ekuahhall@gmail.com | Problem statement: The rise in the use of screens by kids has been known to have negative effects, as reported by the World Health Organization. On the other hand, schools always require tablets or laptops to teach kids coding, AI, and robotics. Solution: Screen-Free all-in-one package consisting of a robot, teacher training web application, logic cards(flashcards), original logic songs, activity books, logic mats, and unplugged games. | Codesrock Labs builds screen-free coding and computational thinking tools for early childhood, ages 3–8. The product ecosystem centers on four pieces that work together inside a school's existing classroom routine rather than replacing it. Rockbot is the physical, programmable robot children command using movement-based logic before they ever type a line of code — kids "act out" sequences with their bodies, then translate that into Rockbot commands, building muscle memory for algorithmic thinking. Logic Flashcards and mats reinforce the same concepts away from the robot, giving teachers a low-tech way to drill concepts like algorithms, digital twins and machines in short bursts. The Curriculum is leveled and structured around modudules grouped into 4 courses — Computational Thinking, Coding Adventures, AI Adventures and Mechazilla Machines — moving children from no technology education experience at age 3 to proficiency in the foundations of programming, AI and mechanics. The Teacher Portal ties it together: session logging, student progress tracking, and access gating for advanced curriculum as schools and teachers level up. The product isn't sold as a one-off kit — it's delivered through a structured school partnership (the institutional kit, currently 5,850₵ per school) that includes teacher training to a certified proficiency standard, hardware setup, co-taught launch sessions, and ongoing quality monitoring. | 1. Ellen Swatson Hall- Co-founder 2. Triumph Tetteh- Co-founder 3. Winnifed Sepenu-Programs Coordinator | Screen-free learning tools and approach that provide compuatational thinking, AI and robotics skills for children. Product and services include: 1. play mats for applying concepts in a kinesthetic way 2. Logic cards 3. Activity books to guide, track and evaluate students 4. RockBot - 3 levels of robots for computational thinking, advanced coding and AI. | - Launch of Codesrock teacher hub - 20% increase in visibility | - cold emailing - running pilots in schools and communities - content creation and targeted ads | The UNICEF Startup Lab has reshaped how Codesrock Labs operates. Being part of the cohort forced a rebuild of parts of the business model itself. We made a viable government-school pricing tier possible alongside the private one, turning institutional trust into a genuine competitive moat that pure hardware competitors like Cubetto and Lego Education can't replicate locally. The program pushed Codesrock to produce rigorous venture diagnostics it didn't have before — unit economics, a 12-month revenue forecast, validation testing — sharpening the case it's now pitching for scale-up capital and manufacturing partnerships. Most concretely, assigning a project supervisor, and holding the team to weekly milestones has built real operational accountability into Codesrock's day-to-day, accelerating execution and improving efficiency across the business in ways that wouldn't have happened on the company's own timeline. | Instagram - codesrock https://www.instagram.com/codesrock/ Linkedin - Codesrock Labs https://www.linkedin.com/company/codesrock-labs/about/?viewAsMember=true

## Dataroom
Startup Name | Do you have a Data Room | Link to Data Room | Platform being used | Notes | Company Documents | [6 empty] | Board of Director Material |  | Financials |  |  | Marketing Materials |  |  | Intellectual Property |  |  | Market Research |  | Sales |  |  | Staff |  |  |  | Technology |  |  |  |  | Count
[5 empty] | Amended and restated articles of incorporation. | Voting agreements | Investor rights agreements | First refusal & co-sale agreements | Stock purchase agreements | Capitalization table | Any documents/details on previous raises (if any) | All board meeting minutes | Board consents and actions | Profit and loss statements | Pro-forma statements for next year | Projections for the next 3 years | One Pager | Pitch Deck | Brand Guidelines & Vision | Granted and filed patents | Trademarks | IP strategy | Market studies | Competitive analysis w/ features & pricing | Sales process | Growth Strategy for the next 5 years | Sales pipeline | List of all current employees, titles and salaries | Employee agreements | Future critical roles and hires | List of contract workers and firms | System architecture diagram | API documentation | Details on any large integrations | Product backlog export and release map | Screenshots of existing products
| NO | [35 empty] | 0